## Project schedule
| Survey Engine project |  |  |  | Project start: | [5 empty] | 2025-03-31
| CSC-17B | Author: |  | Bryan Estrada | Display week: | [5 empty] | 1
[7 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21 | [6 empty] | 2025-04-28 | [6 empty] | 2025-05-05 | [6 empty] | 2025-05-12 | [6 empty] | 2025-05-19
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2025-03-31 to 2025-05-25
 | time axis 2025-03-31 to 2025-05-25
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Phase I
| Complete Gantt Chart | Bryan | 100% | 2025-03-31 | 2025-03-31 | 1
| Project set up | Bryan | 100% | 2025-03-31 | 2025-04-02 | 3
| Design data structure | Bryan | 100% | 2025-04-02 | 2025-04-05 | 4
| Implement survey class | Bryan | 100% | 2025-04-05 | 2025-04-10
| Implement Response Handling | Bryan | 100% | 2025-04-10 | 2025-04-15
| I/O for binary file | Bryan | 100% | 2025-04-15 | 2025-04-22
| Test & Debugging | Bryan | 100% | 2025-04-22 | 2025-04-26 | 5
| UML Diagram | Bryan | 100% | 2025-04-02 | 2025-05-02
| Documentation | Bryan | 100% | 2025-03-31 | 2025-05-04
Phase II
| Set up database | Bryan | 100% | 2025-05-04 | 2025-05-08 | 5
| Create User/Admin interface | Bryan | 70% | 2025-05-06 | 2025-05-11 | 6
| Develop survey interface | Bryan | 10% | 2025-05-11 | 2025-05-18 | 8
| Develop survey backend | Bryan | 30% | 2025-05-04 | 2025-05-18
| Integrate survey interface with backend | Bryan | 5% | 2025-05-18 | 2025-06-07
| UML Diagram | Bryan | 0% | 2025-05-04 | 2025-06-09 | 37
| Documentation | Bryan | 30% | 2025-05-04 | 2025-06-11 | 39
Formulas:
Bryan Estrada = [Bryan Estrada, row above]
Bryan Estrada = [Display week:, row above]
Display week: = [Bryan Estrada]
Display week: = [Bryan Estrada]+2